## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
1 | Yes | Auto Scheduled | Five to Eight Weeks Before Moving | 16 days | Thu 1/01/04 | Thu 1/22/04 |  | 1
2 | Yes | Auto Scheduled | Planning the Move | 3 days | Thu 1/01/04 | Mon 1/05/04 |  | 2 | This section prepares you to plan your move based on your timetable and moving requirements.
3 | Yes | Auto Scheduled | Calculate moving expenses | 1 day | Thu 1/01/04 | Thu 1/01/04 |  | 3 | Expenses may include supplies, movers, rental truck, and deposits and fees for setting up a new residence.
4 | Yes | Auto Scheduled | Determine the best method of moving | 2 days | Fri 1/02/04 | Mon 1/05/04 | 3 | 3 | Moving methods may include hiring moving services, doing it yourself, or combining approaches.
5 | Yes | Auto Scheduled | Create a moving-expense receipt file | 1 day | Fri 1/02/04 | Fri 1/02/04 | 3 | 3
6 | Yes | Auto Scheduled | Create a moving binder | 1 day | Fri 1/02/04 | Fri 1/02/04 | 3 | 3 | Create a binder to store moving plan, important move documentation, and a log of move notes and activities.
7 | Yes | Auto Scheduled | Household Administration | 6 days | Mon 1/05/04 | Mon 1/12/04 |  | 2 | Household administration includes all activities that are required to transfer a household from location to another aside from moving physical items.
8 | Yes | Auto Scheduled | Finances and Insurance | 2 days | Mon 1/05/04 | Tue 1/06/04 |  | 3 | Tasks related to finances and insurance include all changes to banking activity, insurance, and costs of the move.
9 | Yes | Auto Scheduled | Review household finances | 1 day | Tue 1/06/04 | Tue 1/06/04 | 6;4 | 4
10 | Yes | Auto Scheduled | Verify that your belongings are insured for the move | 1 day | Mon 1/05/04 | Mon 1/05/04 | 6 | 4 | Your homeowner or renter's insurance may cover your belongings. Standard insurance coverage from a moving service rarely covers your belongings for replacement value.
11 | Yes | Auto Scheduled | Appraise valuables specifically insured for the move | 2 days | Mon 1/05/04 | Tue 1/06/04 | 6 | 4
12 | Yes | Auto Scheduled | Transfer insurance policies to your new address | 1 day | Mon 1/05/04 | Mon 1/05/04 | 6 | 4 | Instruct your insurance agent to transfer property, fire, and auto insurance.
13 | Yes | Auto Scheduled | Transfer medical insurance to your new location | 1 day | Mon 1/05/04 | Mon 1/05/04 | 6 | 4 | Inform your company's benefit representative of your new address. If you're changing jobs, verify that you are receiving interim health insurance.
14 | Yes | Auto Scheduled | Notifications | 2 days | Tue 1/06/04 | Wed 1/07/04 |  | 3 | Notifications include notifying friends, family, government agencies, magazines you subscribe to, or others who need your new address.
15 | Yes | Auto Scheduled | Notify your employer of your moving dates and new address | 1 day | Tue 1/06/04 | Tue 1/06/04 | 13 | 4
16 | Yes | Auto Scheduled | Transfer, sell, or discontinue any memberships | 2 days | Tue 1/06/04 | Wed 1/07/04 | 13 | 4 | Memberships may include clubs, gyms, organizations, or community groups.
17 | Yes | Auto Scheduled | Vital Services and Records | 2 days | Thu 1/08/04 | Fri 1/09/04 |  | 3 | Vital services may include medical, schools, and veterinary care.
18 | Yes | Auto Scheduled | Organize important records | 2 days | Thu 1/08/04 | Fri 1/09/04 | 16 | 4 | Important records may include prescriptions, optical prescriptions, x-rays, medical and dental records, school records, and birth certificates.
19 | Yes | Auto Scheduled | Contact your doctor, dentist, and vet for referrals | 1 day | Thu 1/08/04 | Thu 1/08/04 | 16 | 4
20 | Yes | Auto Scheduled | Request additional refills of vital medications | 1 day | Thu 1/08/04 | Thu 1/08/04 | 16 | 4
21 | Yes | Auto Scheduled | Your New Residence | 2 days | Fri 1/09/04 | Mon 1/12/04 |  | 3 | Your New Residence includes all activities that will help you get accustomed to your new community or set up your new residence. These activities also include establishing utilities and government services.
22 | Yes | Auto Scheduled | Collect shopping and dining guides from your new community | 2 days | Fri 1/09/04 | Mon 1/12/04 | 20 | 4
23 | Yes | Auto Scheduled | Determine the location of the police, fire department and hospitals | 1 day | Fri 1/09/04 | Fri 1/09/04 | 20 | 4
24 | Yes | Auto Scheduled | Change drivers/vehicle license address if required | 1 day | Fri 1/09/04 | Fri 1/09/04 | 20 | 4
25 | Yes | Auto Scheduled | Place orders for new furniture | 2 days | Fri 1/09/04 | Mon 1/12/04 | 20 | 4
26 | Yes | Auto Scheduled | Moving | 8 days | Tue 1/13/04 | Thu 1/22/04 |  | 2 | Moving encompasses all activities involved in physically moving your possessions from one location to another.
27 | Yes | Auto Scheduled | Movers | 4 days | Tue 1/13/04 | Fri 1/16/04 |  | 3 | Movers refers to all activities done by or in conjunction with a moving service.
28 | Yes | Auto Scheduled | Obtain estimates from several moving services | 4 days | Tue 1/13/04 | Fri 1/16/04 | 25 | 4 | On-site estimates tend to be more accurate and save you from surprises when the movers arrive.
29 | Yes | Auto Scheduled | Request references from each moving service | 1 day | Tue 1/13/04 | Tue 1/13/04 | 25 | 4
30 | Yes | Auto Scheduled | Select moving service | 1 day | Tue 1/13/04 | Tue 1/13/04 | 25 | 4
31 | Yes | Auto Scheduled | Discuss rough details with movers | 1 day | Tue 1/13/04 | Tue 1/13/04 | 25 | 4 | Rough details may include costs, packing requirements, preliminary move dates, and insurance availability.
32 | Yes | Auto Scheduled | Packing | 7 days | Wed 1/14/04 | Thu 1/22/04 |  | 3 | Packing includes all activities in preparing and packing your possessions to be moved.
33 | Yes | Auto Scheduled | Inventory and organize all possessions | 7 days | Wed 1/14/04 | Thu 1/22/04 | 31 | 4 | It is important to decide which possessions will be moved by movers, moved by you, or donated and sold. You should move valuable or irreplaceable items such as legal documents, jewelry, photos, or home videos yourself.
34 | Yes | Auto Scheduled | Begin using food and cleaning supplies currently on hand | 1 day | Wed 1/14/04 | Wed 1/14/04 | 31 | 4 | Avoid shopping for anything you'll have to move.
35 | Yes | Auto Scheduled | Start cleaning closets, bookcases, and other storage areas | 5 days | Wed 1/14/04 | Tue 1/20/04 | 31 | 4
36 | Yes | Auto Scheduled | Conduct a sale or donate to charity | 3 days | Wed 1/14/04 | Fri 1/16/04 | 31 | 4
37 | Yes | Auto Scheduled | Decide what furniture items you want to keep | 4 days | Wed 1/14/04 | Mon 1/19/04 | 31 | 4 | Obtain a floor plan of your new residence if possible.
38 | Yes | Auto Scheduled | Reserve storage if necessary | 1 day | Wed 1/14/04 | Wed 1/14/04 | 31 | 4
39 | Yes | Auto Scheduled | Preparing for Moving Day | 3 days | Thu 1/15/04 | Mon 1/19/04 |  | 3 | Preparing for moving day refers to all activities that will need to be done on the day of the move.
40 | Yes | Auto Scheduled | Make any long distance travel arrangements | 3 days | Thu 1/15/04 | Mon 1/19/04 | 38 | 4 | Arrangements may include airlines, hotels, or car rental. Make sure to make arrangements for your pets.
41 | Yes | Auto Scheduled | Three to Five Weeks Before Moving | 14 days | Tue 1/20/04 | Fri 2/06/04 |  | 1
42 | Yes | Auto Scheduled | Household Administration | 5 days | Tue 1/20/04 | Mon 1/26/04 |  | 2
43 | Yes | Auto Scheduled | Finances and Insurance | 4 days | Tue 1/20/04 | Fri 1/23/04 |  | 3
44 | Yes | Auto Scheduled | Research and choose bank at the new location | 4 days | Tue 1/20/04 | Fri 1/23/04 | 40 | 4
45 | Yes | Auto Scheduled | Open new bank account | 1 day | Tue 1/20/04 | Tue 1/20/04 | 40 | 4
46 | Yes | Auto Scheduled | Order bank checks with your new address | 1 day | Tue 1/20/04 | Tue 1/20/04 | 40 | 4
47 | Yes | Auto Scheduled | Close any local charge accounts | 1 day | Tue 1/20/04 | Tue 1/20/04 | 40 | 4
48 | Yes | Auto Scheduled | Notifications | 3 days | Wed 1/21/04 | Fri 1/23/04 |  | 3
49 | Yes | Auto Scheduled | Schedule disconnection of utilities | 3 days | Wed 1/21/04 | Fri 1/23/04 | 47 | 4 | Utilities to disconnect may include the following: - Water company - Cable TV company - Electric company - Newspaper delivery - Gas/oil company - Dairy delivery - Telephone company Be sure to specify that the final day of service is on (for deliveries such as newspaper or dairy products) or after the move date (utilities).
50 | Yes | Auto Scheduled | Change your address with government agencies if required | 1 day | Wed 1/21/04 | Wed 1/21/04 | 47 | 4
51 | Yes | Auto Scheduled | Clear up any unpaid taxes or parking tickets | 3 days | Wed 1/21/04 | Fri 1/23/04 | 47 | 4 | Contact your local government. These fees may follow you to your new residence.
52 | Yes | Auto Scheduled | Transfer car registration to your new location | 1 day | Wed 1/21/04 | Wed 1/21/04 | 47 | 4
53 | Yes | Auto Scheduled | Vital Services and Records | 3 days | Thu 1/22/04 | Mon 1/26/04 |  | 3
54 | Yes | Auto Scheduled | Register your children in their new schools | 3 days | Thu 1/22/04 | Mon 1/26/04 | 52 | 4
55 | Yes | Auto Scheduled | Forward children's school records to the new school district | 1 day | Thu 1/22/04 | Thu 1/22/04 | 52 | 4
56 | Yes | Auto Scheduled | Your New Residence | 1 day | Fri 1/23/04 | Fri 1/23/04 |  | 3
57 | Yes | Auto Scheduled | Order mailing labels with your new address | 1 day | Fri 1/23/04 | Fri 1/23/04 | 55 | 4
58 | Yes | Auto Scheduled | Determine if there are pet requirements at the new location | 1 day | Fri 1/23/04 | Fri 1/23/04 | 55 | 4
59 | Yes | Auto Scheduled | Schedule move with the building management at the new location | 1 day | Fri 1/23/04 | Fri 1/23/04 | 55 | 4 | Move-in times may be limited. Elevators may need to be scheduled.
60 | Yes | Auto Scheduled | Schedule cable television installation if required | 1 day | Fri 1/23/04 | Fri 1/23/04 | 55 | 4
61 | Yes | Auto Scheduled | Schedule internet installation if required | 1 day | Fri 1/23/04 | Fri 1/23/04 | 55 | 4
62 | Yes | Auto Scheduled | Contact utility companies and sign up for new service | 1 day | Fri 1/23/04 | Fri 1/23/04 | 55 | 4 | Schedule utility connection before your move-in date for: - Water company - Electric company - Gas/oil company - Telephone company
63 | Yes | Auto Scheduled | Moving | 10 days | Mon 1/26/04 | Fri 2/06/04 |  | 2
64 | Yes | Auto Scheduled | Movers | 1 day | Mon 1/26/04 | Mon 1/26/04 |  | 3
65 | Yes | Auto Scheduled | Confirm your move date with your moving service | 1 day | Mon 1/26/04 | Mon 1/26/04 | 62 | 4
66 | Yes | Auto Scheduled | Do-It-Yourself | 3 days | Tue 1/27/04 | Thu 1/29/04 |  | 3 | Do-it-yourself refers to tasks you need to complete if you are making the move on your own or if you are doing any part of the move.
67 | Yes | Auto Scheduled | Reserve a truck or trailer | 1 day | Tue 1/27/04 | Tue 1/27/04 | 65 | 4
68 | Yes | Auto Scheduled | Begin enlisting assistance for moving day | 3 days | Tue 1/27/04 | Thu 1/29/04 | 65 | 4
69 | Yes | Auto Scheduled | Packing | 8 days | Tue 1/27/04 | Thu 2/05/04 |  | 3
70 | Yes | Auto Scheduled | Start collecting boxes, tape, and padding | 8 days | Tue 1/27/04 | Thu 2/05/04 | 65 | 4
71 | Yes | Auto Scheduled | Arrange for disposal of items not sold or donated | 2 days | Fri 1/30/04 | Mon 2/02/04 | 68 | 4
72 | Yes | Auto Scheduled | Begin letting children do some of their own packing and labeling | 4 days | Fri 1/30/04 | Wed 2/04/04 | 68 | 4
73 | Yes | Auto Scheduled | Begin packing books, seasonal clothing, or sporting equipment | 5 days | Fri 1/30/04 | Thu 2/05/04 | 68 | 4
74 | Yes | Auto Scheduled | Send furniture, drapes, and carpets for repair or cleaning | 1 day | Fri 1/30/04 | Fri 1/30/04 | 68 | 4
75 | Yes | Auto Scheduled | Have appliances serviced for moving, if applicable | 2 days | Fri 1/30/04 | Mon 2/02/04 | 68 | 4
76 | Yes | Auto Scheduled | Preparing for Moving Day | 1 day | Fri 2/06/04 | Fri 2/06/04 |  | 3
77 | Yes | Auto Scheduled | Arrange for child care the day of the move | 1 day | Fri 2/06/04 | Fri 2/06/04 | 75;73 | 4 | A friend or sitter can keep children safe during the loading and unloading process.
78 | Yes | Auto Scheduled | One to Two Weeks Before Moving | 10 days | Mon 2/09/04 | Fri 2/20/04 |  | 1
79 | Yes | Auto Scheduled | Household Administration | 5 days | Mon 2/09/04 | Fri 2/13/04 |  | 2
80 | Yes | Auto Scheduled | Finances and Insurance | 2 days | Mon 2/09/04 | Tue 2/10/04 |  | 3
81 | Yes | Auto Scheduled | Transfer your bank accounts to new bank or new location | 1 day | Mon 2/09/04 | Mon 2/09/04 | 77 | 4
82 | Yes | Auto Scheduled | Close existing bank accounts at old location | 1 day | Mon 2/09/04 | Mon 2/09/04 | 77 | 4
83 | Yes | Auto Scheduled | Empty safe-deposit box | 1 day | Mon 2/09/04 | Mon 2/09/04 | 77 | 4
84 | Yes | Auto Scheduled | Organize appliance documents | 1 day | Tue 2/10/04 | Tue 2/10/04 | 83 | 4 | Documents could include warranties, instruction manuals, and receipts.
85 | Yes | Auto Scheduled | Make arrangements to pay for your move | 1 day | Tue 2/10/04 | Tue 2/10/04 | 83 | 4
86 | Yes | Auto Scheduled | Buy traveler's checks | 1 day | Tue 2/10/04 | Tue 2/10/04 | 83 | 4
87 | Yes | Auto Scheduled | Notifications | 3 days | Wed 2/11/04 | Fri 2/13/04 |  | 3
88 | Yes | Auto Scheduled | Fill out mail change of address cards | 3 days | Wed 2/11/04 | Fri 2/13/04 | 86 | 4
89 | Yes | Auto Scheduled | Distribute new address | 1 day | Wed 2/11/04 | Wed 2/11/04 | 86 | 4 | Provide your new address for your - Charge accounts - Credit cards - Loan companies - Subscriptions - Insurance agency - Friends, relatives
90 | Yes | Auto Scheduled | If no longer required, cancel local deliveries | 1 day | Wed 2/11/04 | Wed 2/11/04 | 86 | 4
91 | Yes | Auto Scheduled | Cancel newspaper delivery | 1 day | Wed 2/11/04 | Wed 2/11/04 | 86 | 4
92 | Yes | Auto Scheduled | Take trash to dump or recycling center | 1 day | Wed 2/11/04 | Wed 2/11/04 | 86 | 4
93 | Yes | Auto Scheduled | Coordinate with friend to act as your message center | 2 days | Wed 2/11/04 | Thu 2/12/04 | 86 | 4
94 | Yes | Auto Scheduled | Vital Services and Records | 1 day | Fri 2/13/04 | Fri 2/13/04 |  | 3 | Vital services may include medical professionals, schools, and veterinary care.
95 | Yes | Auto Scheduled | Have medical and dental records forwarded | 1 day | Fri 2/13/04 | Fri 2/13/04 | 93 | 4
96 | Yes | Auto Scheduled | Contact your pharmacist for referral | 1 day | Fri 2/13/04 | Fri 2/13/04 | 93 | 4
97 | Yes | Auto Scheduled | Transfer your prescriptions to this new pharmacy | 1 day | Fri 2/13/04 | Fri 2/13/04 | 93 | 4
98 | Yes | Auto Scheduled | Your New Residence | 1 day | Fri 2/13/04 | Fri 2/13/04 |  | 3
99 | Yes | Auto Scheduled | Contact previous residents for appliance documentation | 1 day | Fri 2/13/04 | Fri 2/13/04 | 93 | 4
100 | Yes | Auto Scheduled | Subscribe to the local newspapers and community newsletters | 1 day | Fri 2/13/04 | Fri 2/13/04 | 93 | 4
101 | Yes | Auto Scheduled | Moving | 5 days | Mon 2/16/04 | Fri 2/20/04 |  | 2
102 | Yes | Auto Scheduled | Movers | 1 day | Mon 2/16/04 | Mon 2/16/04 |  | 3
103 | Yes | Auto Scheduled | Check with mover about moving house plants | 1 day | Mon 2/16/04 | Mon 2/16/04 | 100 | 4 | Some movers will not move plants. It is illegal for mover to move house plants in some locations.
104 | Yes | Auto Scheduled | Obtain moving service contact numbers | 1 day | Mon 2/16/04 | Mon 2/16/04 | 100 | 4
105 | Yes | Auto Scheduled | Acquire labels for boxes (for example, Fragile, Load First, Load Last) | 1 day | Mon 2/16/04 | Mon 2/16/04 | 100 | 4
106 | Yes | Auto Scheduled | Verify that the moving service has your contact numbers | 1 day | Mon 2/16/04 | Mon 2/16/04 | 100 | 4 | Contact numbers should include the lodging numbers if you don't go directly to your new location.
107 | Yes | Auto Scheduled | Give moving service written directions to the new location | 1 day | Mon 2/16/04 | Mon 2/16/04 | 100 | 4
108 | Yes | Auto Scheduled | Do-It-Yourself | 1 day | Tue 2/17/04 | Tue 2/17/04 |  | 3
109 | Yes | Auto Scheduled | Move possessions to storage facility if necessary | 1 day | Tue 2/17/04 | Tue 2/17/04 | 107 | 4
110 | Yes | Auto Scheduled | Confirm assistance for moving day | 1 day | Tue 2/17/04 | Tue 2/17/04 | 107 | 4
111 | Yes | Auto Scheduled | Verify dolly available with truck rental | 1 day | Tue 2/17/04 | Tue 2/17/04 | 107 | 4
112 | Yes | Auto Scheduled | Packing | 3 days | Wed 2/18/04 | Fri 2/20/04 |  | 3
113 | Yes | Auto Scheduled | Clean appliances | 1 day | Wed 2/18/04 | Wed 2/18/04 | 111 | 4
114 | Yes | Auto Scheduled | Pick up all dry cleaning | 1 day | Wed 2/18/04 | Wed 2/18/04 | 111 | 4
115 | Yes | Auto Scheduled | Pack items that you do not use regularly | 3 days | Wed 2/18/04 | Fri 2/20/04 | 111 | 4 | These items can include clothing, books, pots, pans, and kitchenware. Be sure to label all boxes.
116 | Yes | Auto Scheduled | Pack all valuables to move personally | 2 days | Wed 2/18/04 | Thu 2/19/04 | 111 | 4
117 | Yes | Auto Scheduled | Locate hazardous waste disposal sites | 1 day | Wed 2/18/04 | Wed 2/18/04 | 111 | 4
118 | Yes | Auto Scheduled | Drain all fluids from your lawn mower and power tools | 2 days | Wed 2/18/04 | Thu 2/19/04 | 111 | 4
119 | Yes | Auto Scheduled | Dispose of all hazardous household materials | 2 days | Wed 2/18/04 | Thu 2/19/04 | 111 | 4 | Hazardous materials include cleaning fluids, lighter fluid, and aerosols.
120 | Yes | Auto Scheduled | Have mover pack your goods (unless doing it yourself) | 1 day | Wed 2/18/04 | Wed 2/18/04 | 111 | 4
121 | Yes | Auto Scheduled | Pack travel bags and confirm travel arrangements | 1 day | Wed 2/18/04 | Wed 2/18/04 | 111 | 4
122 | Yes | Auto Scheduled | Preparing for Move Day | 2 days | Thu 2/19/04 | Fri 2/20/04 |  | 3
123 | Yes | Auto Scheduled | Have your automobile serviced if you're traveling by car | 1 day | Thu 2/19/04 | Thu 2/19/04 | 121 | 4
124 | Yes | Auto Scheduled | Plan auto route | 1 day | Thu 2/19/04 | Thu 2/19/04 | 121 | 4
125 | Yes | Auto Scheduled | Plan meals that will use up the food in your freezer | 1 day | Thu 2/19/04 | Thu 2/19/04 | 121 | 4
126 | Yes | Auto Scheduled | Empty, defrost, and clean refrigerator and freezer | 2 days | Thu 2/19/04 | Fri 2/20/04 | 121 | 4
127 | Yes | Auto Scheduled | Prepare a survival kit for move day | 1 day | Thu 2/19/04 | Thu 2/19/04 | 121 | 4 | Your survival kit may include snacks, beverages, and children's games for the trip.
128 | Yes | Auto Scheduled | Prepare your pet's survival kit | 1 day | Thu 2/19/04 | Thu 2/19/04 | 121 | 4 | Your pet may need food, water bowl, toys, and bedding.
129 | Yes | Auto Scheduled | Prepare an immediate-need kit for move day | 2 days | Thu 2/19/04 | Fri 2/20/04 | 121 | 4 | You may need items such as the following: - Telephone - Light bulbs - Tool kit - Scissors - Flashlight - Large trash bags - Paper towels - Toilet paper - Linens to make your beds
130 | Yes | Auto Scheduled | Day of the Move | 1 day | Mon 2/23/04 | Mon 2/23/04 |  | 1
131 | Yes | Auto Scheduled | Old Residence | 1 day | Mon 2/23/04 | Mon 2/23/04 |  | 2
132 | Yes | Auto Scheduled | Moving | 1 day | Mon 2/23/04 | Mon 2/23/04 |  | 3
133 | Yes | Auto Scheduled | Have tools, tape, twine, and spare boxes on hand | 1 day | Mon 2/23/04 | Mon 2/23/04 | 129 | 4
134 | Yes | Auto Scheduled | Be present throughout the entire move | 1 day | Mon 2/23/04 | Mon 2/23/04 | 129 | 4
135 | Yes | Auto Scheduled | Verify all possessions have been packed and loaded | 1 day | Mon 2/23/04 | Mon 2/23/04 | 129 | 4 | Verify that everything is packed and loaded before the moving service leaves the premises.
136 | Yes | Auto Scheduled | Make sure fragile items are handled carefully | 1 day | Mon 2/23/04 | Mon 2/23/04 | 129 | 4
137 | Yes | Auto Scheduled | Pack cleaning supplies including a vacuum cleaner in a box labeled Last Load | 1 day | Mon 2/23/04 | Mon 2/23/04 | 129 | 4
138 | Yes | Auto Scheduled | Verify that bedding gets packed last | 1 day | Mon 2/23/04 | Mon 2/23/04 | 129 | 4
139 | Yes | Auto Scheduled | New Residence | 1 day | Mon 2/23/04 | Mon 2/23/04 |  | 2
140 | Yes | Auto Scheduled | Household Administration | 1 day | Mon 2/23/04 | Mon 2/23/04 |  | 3
141 | Yes | Auto Scheduled | Empty, defrost, and clean the new refrigerator | 1 day | Mon 2/23/04 | Mon 2/23/04 | 129 | 4
142 | Yes | Auto Scheduled | Designate a room for your pet | 1 day | Mon 2/23/04 | Mon 2/23/04 | 129 | 4
143 | Yes | Auto Scheduled | Have snacks and beverages on hand throughout the day | 1 day | Mon 2/23/04 | Mon 2/23/04 | 129 | 4
144 | Yes | Auto Scheduled | Moving | 1 day | Mon 2/23/04 | Mon 2/23/04 |  | 3
145 | Yes | Auto Scheduled | Be present throughout the entire move | 1 day | Mon 2/23/04 | Mon 2/23/04 | 129 | 4 | If you can't be present yourself, designate another adult to be present with the moving service.
146 | Yes | Auto Scheduled | Make sure fragile items are handled carefully | 1 day | Mon 2/23/04 | Mon 2/23/04 | 129 | 4
147 | Yes | Auto Scheduled | Review all paperwork when the moving service arrives | 1 day | Mon 2/23/04 | Mon 2/23/04 | 129 | 4
148 | Yes | Auto Scheduled | Pay moving service before unpacking | 1 day | Mon 2/23/04 | Mon 2/23/04 | 129 | 4
149 | Yes | Auto Scheduled | Check carefully for any damaged or missing items | 1 day | Mon 2/23/04 | Mon 2/23/04 | 129 | 4
150 | Yes | Auto Scheduled | Read and sign bill of lading | 1 day | Mon 2/23/04 | Mon 2/23/04 | 129 | 4
151 | Yes | Auto Scheduled | Retain copies of the bill of lading and inventory | 1 day | Mon 2/23/04 | Mon 2/23/04 | 129 | 4
152 | Yes | Auto Scheduled | Move completed | 0 days | Mon 2/23/04 | Mon 2/23/04 | 151 | 4
153 | Yes | Auto Scheduled | One to Two Weeks After the Move | 5 days | Tue 2/24/04 | Mon 3/01/04 |  | 1
154 | Yes | Auto Scheduled | Household Administration | 5 days | Tue 2/24/04 | Mon 3/01/04 |  | 2
155 | Yes | Auto Scheduled | Finances and Insurance | 1 day | Tue 2/24/04 | Tue 2/24/04 |  | 3
156 | Yes | Auto Scheduled | Put valuables into a safety deposit box in the new bank | 1 day | Tue 2/24/04 | Tue 2/24/04 | 152 | 4
157 | Yes | Auto Scheduled | Notifications | 2 days | Wed 2/25/04 | Thu 2/26/04 |  | 3
158 | Yes | Auto Scheduled | Arrange for new registration of cars (bicycles also, if required) | 1 day | Wed 2/25/04 | Wed 2/25/04 | 156 | 4
159 | Yes | Auto Scheduled | Have pets licensed | 1 day | Thu 2/26/04 | Thu 2/26/04 | 158 | 4
160 | Yes | Auto Scheduled | Change your voter registration, if required | 1 day | Thu 2/26/04 | Thu 2/26/04 | 158 | 4
161 | Yes | Auto Scheduled | Vital Services and Records | 1 day | Fri 2/27/04 | Fri 2/27/04 |  | 3
162 | Yes | Auto Scheduled | Contact new dentists and doctors to verify record delivery | 1 day | Fri 2/27/04 | Fri 2/27/04 | 160 | 4
163 | Yes | Auto Scheduled | Get recommendations for babysitters, nanny agencies, and other services | 1 day | Fri 2/27/04 | Fri 2/27/04 | 160 | 4
164 | Yes | Auto Scheduled | Verify that new schools have received records | 1 day | Fri 2/27/04 | Fri 2/27/04 | 160 | 4
165 | Yes | Auto Scheduled | Update driver's license and car license plates | 1 day | Fri 2/27/04 | Fri 2/27/04 | 160 | 4
166 | Yes | Auto Scheduled | Your New Residence | 1 day | Mon 3/01/04 | Mon 3/01/04 |  | 3
167 | Yes | Auto Scheduled | Make additional sets of keys and change locks if necessary | 1 day | Mon 3/01/04 | Mon 3/01/04 | 165 | 4
168 | Yes | Auto Scheduled | Ask for repair service recommendations | 1 day | Mon 3/01/04 | Mon 3/01/04 | 165 | 4
169 | Yes | Auto Scheduled | Meet your neighbors (write down their names) | 1 day | Mon 3/01/04 | Mon 3/01/04 | 165 | 4
170 | Yes | Auto Scheduled | Find out about recycling at the new location | 1 day | Mon 3/01/04 | Mon 3/01/04 | 165 | 4
171 | Yes | Auto Scheduled | Enjoy your new home | 0 days | Mon 3/01/04 | Mon 3/01/04 | 170 | 1

## Resource_Table
ID | Indicators | Resource name | Type | Material label | Initials | Group | Max.Units | Std.Rate | Ovt.Rate | Cost/Use | Accrue At | Base Calendar | Code

## Assignment_Table
ID | Task name | Resource name | Work | Duration